## Project Planner
Project Planner
[5 empty] | Period Highlight: | 8 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week Number
[6 empty] | 2017-04-03 |  |  |  | 2017-05-01 |  |  |  |  | 2017-06-05 |  |  |  | 2017-07-03 |  |  |  |  | 2017-08-07 |  |  |  | 2017-09-04 |  |  |  | 2017-10-02 |  |  |  |  | 2017-11-06 |  |  |  | 2017-12-04 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-05 |  |  |  | 2018-03-05 |  |  | 2018-03-26 | 2018-04-02 | 2018-04-09
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
WP1 – Innovation | 1 | 12 |  |  | 100%
Collate and clean data | 1 | 2 |  |  | 0%
Classification of barriers | 2 | 4 |  |  | 100%
Filtering of barriers | 6 | 2 |  |  | 60%
Identify interventions | 8 | 2 |  |  | 0%
Cost estimation | 10 | 2 |  |  | 0%
Effectiveness estimation | 10 | 3 |  |  | 0%
Work Package 1 Report | 12 | 1 |  |  | 0%
WP2 – Feedback and refinement | 13 | 12 |  |  | 0%
Validation against known interventions | 13 | 4 |  |  | 0%
Expert and practitioner feedback | 13 | 8 |  |  | 0%
Refinement of methods | 19 | 6 |  |  | 0%
Work Package 2 Report | 24 | 1
WP3 – National deployment | 24 | 29 |  |  | 0%
Optimisation of algorithms | 24 | 6 |  |  | 0%
Collate and clean data | 26 | 6 |  |  | 0%
Filtering of barriers | 30 | 6 |  |  | 0%
Identify interventions | 34 | 6 |  |  | 0%
Interim Report | 36 | 1 |  |  | 0%
Cost estimation | 38 | 6 |  |  | 0%
Effectiveness estimation | 42 | 8 |  |  | 0%
Visualise results | 45 | 6 |  |  | 0%
Export data products | 26 | 25
Complete documentation and write-up | 38 | 15
Training and Dissemination | 51 | 2
Final report | 48 | 5