Project planner uses periods for intervals. Start=1 is period 1 and duration=5 means project spans 5 periods starting from start period. Enter data starting in B5 to update the chart
Title of the project. Enter a new title in this cell. Highlight a period in H2. Chart legend is in J2 to AI2
Select a period to highlight in H2. A Chart legend is in J2 to AI2
Enter activity in column B, starting with cell B5
Enter plan start period in column C, starting with cell C5
Enter plan duration period in column D, starting with cell D5
Enter actual start period in column E, starting with cell E5
Enter actual duration period in column F, starting with cell F5
Enter the percentage of project completed in column G, starting with cell G5
Enter a period in the range of 1 to 60 or select a period from the list. Press ALT+DOWN ARROW to navigate the list, then ENTER to select a value
Type a value from 1 to 60 or select a period from the list-press CANCEL, ALT+DOWN ARROW, then ENTER to select a value
Periods are charted from 1 to 60 starting from cell H4 to cell BO4
This legend cell indicates the percentage of project completed
This legend cell indicates plan duration
This legend cell indicates actual duration
This legend cell indicates actual duration beyond plan
This legend cell indicates the percentage of project completed beyond plan
## Project Planner
Project Planner
					Period Highlight:	5			Plan Duration					Actual Start					% Complete					Actual (beyond plan)					% Complete (beyond plan)
	PLAN START	PLAN DURATION	ACTUAL START	ACTUAL DURATION	PERCENT COMPLETE	Week Number
					2017-04-03				2017-05-01					2017-06-05				2017-07-03					2017-08-07				2017-09-04				2017-10-02					2017-11-06				2017-12-04				2018-01-01					2018-02-05				2018-03-05			2018-03-26	2018-04-02	2018-04-09
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54
WP1 – Innovation	1	12			100%
Collate and clean data	1	2			100%
Classification of barriers	2	4			100%
Filtering of barriers	6	2			60%
Identify interventions	8	2			0%
Cost estimation	10	2			0%
Effectiveness estimation	10	3			0%
Work Package 1 Report	12	1			0%
WP2 – Feedback and refinement	13	12			0%
Validation against known interventions	13	4			0%
Expert and practitioner feedback	13	8			0%
Refinement of methods	19	6			0%
Work Package 2 Report	24	1
WP3 – National deployment	24	29			0%
Optimisation of algorithms	24	6			0%
Collate and clean data	26	6			0%
Filtering of barriers	30	6			0%
Identify interventions	34	6			0%
Interim Report	36	1			0%
Cost estimation	38	6			0%
Effectiveness estimation	42	8			0%
Visualise results	45	6			0%
Export data products	26	25
Complete documentation and write-up	38	15
Training and Dissemination	51	2
Final report	48	5